## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 33
PROJECT NAME | Computer Vision Application for Real-time Multimodal Product Detection
PROJECT MENTOR (sponsor) | Chaitanya Sagar
TEAM MEMBERS | Chetan Mahipal
Aanvik Bhatnagar
Rohan S Rathee
Rohan Naidu
Rohan Shridhar

## Status
PROJECT NUMBER | 33
PROJECT NAME | Computer Vision Application for Real-time Multimodal Product Detection
PROJECT MENTOR (sponsor) | Chaitanya Sagar
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | TA
GIT Repository setup | Preparation | TA
Client meeting-1 | Coordination | Aanvik | 5 | 4 | Done | 17-01-24: Make sure scoping questions are included
MoM Client Meet-1 | Documentation | Rohan Sh | 1 | 0.5 | Done |  | 0.5 | 12.5
Get account and configure website | Preparation | Rohan N | 1.5 | 1 | Done | Looking into the client website and understanding their role | 0.5 | 50
Research existing technology | Preparation | Chetan | 2 | 1.5 | Ongoing | Prepared all the possible questionnaire for the first meet with the client | 0.5 | 33.3333
Project synopsis writeup | Documentation | Rohan S | 2 |  | Planned
Identify role owners | Preparation | Rohan S | 1 |  | Planned | Multiple roles are OK - think about role & reponsibility distribution
Team Meeting | Coordination | Aanvik | 1 | 2 | Done | Discussed what schedule for team meets should be kept and work to be done before next client meet | -1 | 50
Client meeting-2 | Coordination | Chetan | 5 | 4 | Done | 19-01-24: Discussed about the previous app and doc details shared at company's end | 1 | 25
MoM Client Meet-2 | Documentation | Aanvik | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Rohan N | 1 |  | Planned
Week 2 (January 22 - January 28)
Client meeting-3 | Coordination | Rohan N | 4 | 4 | Done | 22-01-24: Discussed about the objectives of the project, and suggestions regarding deployment of the app | 0 | 0
MoM Client Meet-3 | Documentation | Aanvik | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Rohan S | 5 | 5 | Done | Discussed points to be raised in client meet, and schedule for the next meet | 0 | 0
Develop questions for requirements elicitation | Documentation | Chetan | 2 | 2.5 | Done | Make sure scoping questions are included | -0.5 | 20
Status tracker | Documentation | Rohan N | 2 | 2 | Done | Status Tracker has been configured, and link has been submitted to the TA | 0 | 0
Client meeting-4 | Coordination | Rohan Sh | 5 | 5.5 | Done | 24-01-24: Need to write a misson statement, divide team into frontend and backend. | -0.5 | 9.0909
MoM Client Meet-4 | Documentation | Aanvik | 1 | 1 | Done |  | 0 | 0
Identify role owners | Preparation | Chetan | 7.5 |  | Planned | We need to conduct a whole team meet in the upcoming week, where we go through the current objectives of the client and assign whatever suits best to the individual members.
Project synopsis writeup | Documentation | Aanvik | 2 | 2.5 | Done |  | -0.5 | 20
Codebase check | Preparation | Rohan S | 7.5 |  | Planned | Need to start going through code of the current deployed app, and understand what languages we need to learn for future
Mission Statement writeup | Documentation | Rohan Sh | 5 |  | Planned | Draft 1 required by the client by end of this week, and formal draft in the next week
Week 3 (January 29 - February 4)
Identify role owners | Preparation | Chetan | 7.5 | 4 | Ongoing | Divided the team into frontend (3) and backend (2) team since client requested to do so. | 3.5 | 87.5
Codebase check | Preparation | Rohan S | 7.5 | 4 | Ongoing | Codebase is built of react native and flask envt. Need to develop upon these languages for further development | 3.5 | 87.5
Mission Statement writeup | Documentation | Rohan Sh | 5 | 4 | Done | Uploaded v1 of mission statement for all the members on Slack | 1 | 25
Client meeting-5 | Coordination | Aanvik | 5 | 6 | Done | 01-02-24: Disucussion of individual mission statements and future architecture plan | -1 | 16.6667
MoM Client Meet-5 | Documentation | Rohan N | 1 | 0.5 | Done | Points on structure and use of mission statements, mock-up design | 0.5 | 100
Client meeting-6 | Coordination | Rohan N | 5 | 5 | Done | 02-02-24: Discussed on how to remove the issues to run the app on local machines, | 0 | 0
MoM Client Meet-6 | Documentation | Rohan Sh | 1 | 0.5 | Done | Points on flask, AWS credentials and mock-up design | 0.5 | 100
Team Meeting | Coordination | Rohan S | 4 | 3 | Done | Temporary change in team division for initial UI design, decision on dates for architecture planning | 1 | 33.3333
Reseach on App Architecture and Existing Technology | Preparation | Chetan | 3 |  | Planned | Understand what the definition of app architecture is, and what would be preferred while creating app architecture for this project
Basic Design Layout | Design | Rohan Sh | 5 |  | Planned | Create a UI design on Figma
Final Deliverables Check | Requirements | Aanvik | 2 |  | Planned | Based on mission statements, and client feedback, decide the final deliverables
Week 4 (February 5 - February 12)
Reseach on App Architecture | Preparation | Chetan | 4 | 3 | Ongoing | Explore alternatives to flask, review structure of app | 1 | 33.3333
Basic Design Layout | Design | Rohan S | 6 | 5 | Done | Made a mock-up design of app layout on figma | 1 | 20
Final Deliverables Check | Requirements | Aanvik | 2 | 1 | Ongoing | Final review of deliverables, revision in architecture plan | 1 | 100
Client meeting-7 | Coordination | Chetan | 5 | 5 | Done | 05-02-24: Overviw of individual mission statements, flask-django tradeoff research, Points on researching of architecture design for the app, preparing draft design for next meet | 0 | 0
MoM Client Meet-7 | Documentation | Rohan Sh | 1 | 1 | Done |  | 0 | 0
Client meeting-8 | Coordination | Rohan N | 5 | 5 | Done | 07-02-24: Points on suggested changes in draft design (font, text placement, colour contrast). Figma design overview, suggested changes | 0 | 0
MoM Client Meet-8 | Documentation | Rohan S | 1 | 1 | Done |  | 0 | 0
App Architecture Diagram | Documentation | Aanvik | 3 |  | Planned
Design Layout v2 | Design | Rohan N | 7.5 |  | Planned
Week 5 (February 13 - February 20)
App Architecture Diagram | Documentation | Aanvik | 3 | 2.5 | Done | Overall view has been created, need to detail it later on. | 0.5 | 20
Design Layout v2 | Design | Rohan Sh | 7.5 | 7 | Done | Made changes in the dashboard, and homescreen for order display, looked upto some common ecomm apps to understand common design features | 0.5 | 7.1429
Client meeting-9 | Coordination | Rohan S | 4 | 4 | Done | 12-02-24: Asked to make design improvements in v1, and give cost analysis of AWS | 0 | 0
MoM Client Meet-9 | Documentation | Rohan Sh | 1.5 | 1.5 | Done |  | 0 | 0
Team Meeting | Coordination | Chetan | 4 | 4 | Done | Decisions made to make changes in design v1, and how and where the codebase resides for ML algo, and the AWS instance | 0 | 0
Client meeting-10 | Coordination | Rohan N | 5 | 5 | Done | 14-02-24: Design Changes, scroll down option, and find alternatives to AWS instead. | 0 | 0
MoM Client Meet-10 | Documentation | Rohan N | 1 | 1 | Done |  | 0 | 0
Final Deliverables Check | Requirements | Aanvik | 1 | 2 | Done | Need to discuss with client and team more on how to proceed with final deliverables | -1 | 50
Research existing technology | Preparation | Chetan | 2 | 2 | Ongoing | Existing Cloud Services, and how to deploy our codebase onto it. | 0 | 0
Cost Analysis of AWS v1 | Preparation | Aanvik | 2 | 2 | Done | Comparison of AWS with other cloud providing services, and why AWS is preferred for deployment. | 0 | 0
Figma Design Layout v2 | Design | Rohan Sh | 3 | 3 | Done | Figma Layout for design v2, to be displayed in client meet 10 | 0 | 0
Design Layout v3 | Design | Rohan N | 5 |  | Planned
Client meeting-11 | Coordination | Chetan | 5 | 5 | Done | 16-02-24: Discussed about inputs on the task bar below, and keep multiple versions in handy for items page and home page. Start coding of these two pages. | 0 | 0
MoM Client Meet-11 | Documentation | Chetan | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Rohan S | 4 | 5 | Done | Need to discuss what to include in SRS and how to start with the coding aspects of the project | -1 | 20
SRS Document v1 | Documentation | All | 10 |  | Planned
Test Plan Tracker v1 | Testing | Rohan S | 3 |  | Planned
Cloud Services Alternatives | Preparation | Chetan | 3 |  | Planned
Week 6 (February 21 - February 28)
Design Layout v3 | Design | Rohan N | 5 | 4 | Ongoing | Need to implement the new home page | 1 | 25
SRS Document v1 | Documentation | All | 10 | 12 | Done | SRS v1 sent to client for approval, uploaded on github. | -2 | 16.6667
Test Plan Tracker v1 | Testing | Chetan | 3 |  | Done | Submitted on 22-02-24 based on the updated requirements of client
Cloud Services Alternatives | Preparation | Chetan | 3 | 2 | Ongoing | Working on differences in costing as well as efficiency between Digital Ocean and AWS | 1 | 50
Client meeting-12 | Coordination | Rohan S | 5 | 5 | Done | 19-02-24: Final changes asked to be made in UI | 0 | 0
MoM Client Meet-12 | Documentation | Rohan S | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Chetan | 5 | 5 | Done | Need to discuss how to proceeed with new client requirements, and accordingly start updating the docs | 0 | 0
Client meeting-13 | Coordination | Aanvik | 5 | 4 | Done | 20-01-24: Urgent meet called to discuss inputs on final design changes. Only need to implement Home Page, with major design changes | 1 | 25
MoM Client Meet-13 | Documentation | Rohan S | 1 | 1 | Done |  | 0 | 0
Implementation-Home Page | Development | Rohan N | 4 |  | Delayed | We need to get confirmations from client on what they need to change for home page
Implementation-Items Page | Development | Rohan Sh | 4 |  | Delayed | Major design changes requested by client, possibility of not implementing this at all
Research existing technology | Preparation | Chetan | 3 | 2 | Ongoing | Look into React Native, and Flask frameworks | 1 | 50
Client meeting-14 | Coordination | Aanvik | 5 | 5 | Done | 23-02-24: Need to make the timeline for the upcoming week, start testing cloud services. | 0 | 0
MoM Client Meet-14 | Documentation | Aanvik | 1 | 1 | Done |  | 0 | 0
SRS Document v2 | Documentation | Aanvik | 5 | 2 | Ongoing | Making changes to use cases, and user case description. | 3 | 150
Project Plan v2 | Documentation | Chetan | 3 |  | Planned
Application Running on Local Hosts | Preparation | All | 5 |  | Planned
Week 7 (February 29 - March 6)
Design Layout v3 | Design | Rohan N | 2 | 2 | Done |  | 0 | 0
Cloud Services Alternatives | Preparation | Chetan | 2 | 1 | Ongoing | Credentials for DigitalOcean given to us, need to run the app on the instance once. | 1 | 100
SRS Document v2 | Documentation | Aanvik | 3 | 1 | Ongoing |  | 2 | 200
Implementation- Home Page | Development | Rohan S | 4 | 1 | Ongoing | Final review of figma design given, implementation started for the same | 3 | 300
Project Plan v2 | Documentation | Chetan | 3 | 1 | Ongoing |  | 2 | 200
Application Running on Local Hosts | Preparation | All | 5 | 5 | Done |  | 0 | 0
Timeline for the remaining tasks | Preparation | Aanvik | 2 | 1 | Ongoing | Need to discuss with UI team about their tentative plan | 1 | 100
Client meeting-15 | Coordination | Rohan Sh | 5 | 5 | Done | 01-03-24: Given us final reviews for design, need to start implementing, and timeline to be created on discussion with UI team | 0 | 0
MoM Client Meet-15 | Documentation | Aanvik | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Chetan | 5 | 5 | Done | Need to make sure everyone has run the app on their local hosts, and understand the codebase for the same | 0 | 0
Week 8 (March 7 - March 14)
Cloud Services Alternatives | Preparation | Aanvik | 2
SRS Document v2 | Documentation | Aanvik | 2
Implementation- Home Page | Development | Rohan Sh | 3
Project Plan v2 | Documentation | Chetan | 2
Timeline for the remaining tasks | Preparation | Aanvik | 1
Code flow testing | Testing | Chetan | 5
Testing- Home Page | Testing | Rohan N | 3
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically